Resource Intensive: Implementing a risk management framework requires allocating significant resources, including time, personnel, and financial investment.
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